## Sheet1
task | person 1 | person 2 | person 3 | Everyone pick tasks that you would | scraping shouldnt be too hard
scrape website ESPN csv | Jon |  |  | like to work on. not every task needs | We have learned how to clean data already
scrape website PFR to csv | Kim |  |  | three people but I know some of us | We have also gone over in class how to import data to mongo
clean data | Kim | Paul |  | have limited availability to work and | We are learning how to incorperate html with flask on tuesday
Don't want team name to weeks
Keep identifiable data out so it's in 2nd normal form
Team ID/Team Name
break into each week for attendance and win/loss
do that per year so the Team ID and Team name are the universal connector between everything
import to SQL and ER diagram | Tana |  |  | areas that we are most comfortable | Video link to a sample flask blog site that also incorporates html wtih flask
make flask app/api | Jon | Tana |  | with. | https://youtu.be/MwZwr5Tvyxo
connect to AWS | Jon |  |  |  | There is a lot of AWS support videos out there and it looks like we are doing more AWS in office hours this week in class
make pretty html/css | Tana |  |  |  | HTML and css dolling up of the html added to flask
With the way work is split now there are 21
|  |  |  | tasks to do. 4 each and probably some extras to | This is seeming ambitious but I think we should be able to finish in 1 week provided we can the data quickly. The html and css will be the most tedious part but we can break up the css based on class and id tags
find out about later. Scraping needs to be done asap
once we get approval to start working. Cleaning and
|  |  |  | the flask building are dependent on that. The flask app | Adding everything to AWS will be technical but achievable I think.
can be started as soon as the data structure is decided
upon